## KY Approved Funding Changes
Project Sponsor: | Louisville Metro | KIPDA ID: | 2087 | State ID: | 5-523.00
County: | Jefferson | Parent ID: | N/A | Group ID: | N/A
Project Name: | Dodge Gap Jefferson Memorial Forest (JMF) - Louisville Loop Shared Use Path | Funding Source: | CRP-MPO | Open to Public Date: | 2028
Total Estimated Project Cost: | 10719959 |  | Total Cost Programmed in TIP to date: | $170,000 $292,943
Description: | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Blevins Gap Road to north end of sand quarry tunnel at Gene Snyder Freeway (the tunnel will be part of this segment), approximately 2.5 miles.
Justification: | Improve mobility for non-motorized travel for pedestrians, bicyclists, transit users and equestrians. Connect neighborhoods, schools, parks, workplaces and shopping areas to the Loop where possible. Encourage a wide range of users including families, children, people with disabilities, and athletes to improve their health and fitness. Celebrate the natural and cultural history of Louisville.
FY 23-26 TIP Funding: | FY 2025 Design (D) phase with CRP-MPO funds: $98,354 (Federal) + $24,589 (Other) = $122,943 (Total) FY 2025 Right of Way (ROW) phase with CRP-MPO funds: $111,000 (Federal) + $27,750 (Other) = $138,750 (Total) *FY 2027 Utilities (U) phase with CRP-MPO funds: $25,000 (Federal) + $6,250 (Other) = $31,250 (Total)
Project Sponsor: | Louisville Metro | KIPDA ID: | 1109 | State ID: | 5-505.00
County: | Jefferson | Parent ID: | N/A | Group ID: | N/A
Project Name: | Ohio River Levee Trail Phase III | Funding Source: | CRP-MPO | Open to Public Date: | 2026
Total Estimated Project Cost: | $9,583,895 $9,858,895 |  | Total Cost Programmed in TIP to date: | $9,583,895 $9,858,895
Description: | Construct bicycle/pedestrian facilities along Campground Road from the end of the shared use path at the railroad crossing on Campground Road near I-264 to Lees Lane and the connection to Riverside Gardens Park at 2899 Lees Lane.
Justification: | Completing the ORLT will allow non-motorized travel from downtown Louisville to southwest Jefferson County. This project will complete the second phase of the ORLT by construction a 2.2 mile segment of the shared use path in west Jefferson County near the Ohio River and a rest area overlooking the Ohio River. When all phases of the trail are completed, it will link southwest and west Jefferson County to the RiverWalk Trail that runs from near Chickasaw Park to downtown Louisville and the trails from east to the downtown area. This project will provide a valuable link for non-motorized travel in the Louisville Metro area, connecting neighborhoods while providing access to commercial and opportunities.
FY 23-26 TIP Funding: | FY 2025 Design (D) phase with CRP-MPO funds: $220,000 (Federal) + $55,000 (Other) = $275,000 (Total) FY 2025 Construction (C) phase with CRP-MPO funds: $6,463,000 (Federal) + $1,615,750 (Other) = $8,078,750 (Total)
Project Sponsor: | Louisville Metro | KIPDA ID: | 2979 | State ID: | 5-3036.00
County: | Jefferson | Parent ID: | N/A | Group ID: | N/A
Project Name: | Ohio River Valley NE Bike/Ped Improvements Phase I (Louisville Loop) | Funding Source: | CRP-MPO | Open to Public Date: | 2030
Total Estimated Project Cost: | 8235702 |  | Total Cost Programmed in TIP to date: | $1,250,000 $4,700,000
Description: | Design and construct an accessible shared-use path system, including amenities, that connects the Lewis & Clark Bridge to US 42 in Prospect. This corridor is approximately 2.5 miles of the 100+ mile Louisville Loop.
Justification: | The Ohio River Valley Northeast corridor of the Loop will provide an accessible shared-use path system to allow pedestrians and bicyclists to safely connect from neighborhoods to parks, schools, workplaces, and other community facilities on mostly off-road facilities. It will provide safe alternative transportation routes for pedestrians and bicyclists such as younger children and families who prefer not to ride on the road. On-street bike facilities will also be incorporated where possible to accommodate more experienced riders who prefer to ride on roadways, because the Loop intends to serve all categories of bicyclists.
FY 23-26 TIP Funding: | *FY 2027 Construction (C) Phase with CRP-MPO Funds: $1,000,000 (Federal) + $250,000 (Other) = $1,250,000 (Total) *FY 2029 Construction (C) Phase with CRP-MPO Funds: $3,760,000 (Federal) + $940,000 (Other) = $4,700,000 (Total)
Project Sponsor: | Louisville Metro | KIPDA ID: | 2980 | State ID: | 5-584.00
County: | Jefferson | Parent ID: | N/A | Group ID: | N/A
Project Name: | Ohio River Valley NE Bike/Ped Improvements Phase II (Louisville Loop) | Funding Source: | CRP-MPO | Open to Public Date: | 2028 2029
Total Estimated Project Cost: | $1,812,500 $4,187,500 |  | Total Cost Programmed in TIP to date: | $1,437,500 $4,187,500
Description: | Design and construct an accessible shared-use path system, including amenities; and make improvements to portions of an existing shared-use path that connects the Big Four Bridge to Caperton Swamp. This corridor is approximately 3.5 miles of the 100+ mile Louisville Loop.
Justification: | The Ohio River Valley Northeast corridor of the Loop will provide an accessible shared-use path system to allow pedestrians and bicyclists to safely connect from neighborhoods to parks, schools, workplaces, and other community facilities on mostly off-road facilities. It will provide safe alternative transportation routes for pedestrians and bicyclists such as younger children and families who prefer not to ride on the road. On-street bike facilities will also be incorporated where possible to accommodate more experienced riders who prefer to ride on roadways, because the Loop intends to serve all categories of bicyclists.
FY 23-26 TIP Funding: | FY 2025 Design (D) phase with CRP-MPO funds: $550,000 (Federal) + $137,500 (Other) = $687,500 (Total) FY 2026 Right of Way (ROW) Phase with CRP-MPO Funds: $88,000 (Federal) + $22,000 (Other) = $110,000 (Total) FY 2026 Utilities (U) Phase with CRP-MPO Funds: $28,000 (Federal) + $7,000 (Other) = $35,000 (Total) FY 2026 Construction (C) Phase with STBG-MPO Funds: $1,150,000 (Federal) + $287,500 (Other) = $1,437,500 (Total) *FY 2028 Construction (C) Phase with CRP-MPO Funds: $2,696,000 (Federal) + $659,000 (Other) = $3,355,000 (Total)
Project Sponsor: | Louisville Metro | KIPDA ID: | 3308 | State ID: | 5-478.81
County: | Jefferson | Parent ID: | 3181 | Group ID:
Project Name: | Dixie Highway Streetscape - Maple to Garland | Funding Source: | CRP-MPO | Open to Public Date: | 2026
Total Estimated Project Cost: | $2,178,750 $2,238,750 |  | Total Cost Programmed in TIP to date: | $2,178,750 $2,238,750
Description: | Construction of streetscape improvements along Dixie Highway from just north of Maple Street to Garland Avenue, including bicycle and pedestrian facilities, and street lighting.
Justification: | Streetscape improvements should transform the vehicular and pedestrian spaces into an attractive urban space that can serve cars, bikes, and people. The design should accommodate and enhance the variety of properties in the neighborhood, including housing, retail, restaurant, manufacturing, and office uses.
FY 23-26 TIP Funding: | FY 2025 Right of Way (ROW) phase with CRP-MPO funds: $48,000 (Federal) + $12,000 (Other) = $60,000 (Total) FY 2026 Construction (C) phase with CRP-MPO funds: $1,743,000 (Federal) + $435,750 (Other) = $2,178,750 (Total)
Project Sponsor: | Louisville Metro | KIPDA ID: | 2092 | State ID: | 5-524.00
County: | Jefferson | Parent ID: | 1857 | Group ID:
Project Name: | Medora Jefferson Memorial Forest (IMF) - Louisville Loop Shared Use Path | Funding Source: | TA-MPO | Open to Public Date: | 2026
Total Estimated Project Cost: | $5,740,672 $6,645,672 |  | Total Cost Programmed in TIP to date: | $5,740,672 $6,645,672
Description: | Design and construct shared use path and Louisville Loop trailhead facilities through Jefferson Memorial Forest from Pendleton Road at Medora Road to the beginning of Jefferson Memorial Forest property on Blevins Gap Road, approximately 1.3 miles.
Justification: | Improve mobility for non-motorized travel for pedestrians, bicyclists, transit users and equestrians. Connect neighborhoods, schools, parks, workplaces and shopping areas to the Loop where possible. Encourage a wide range of users including families, children, people with disabilities, and athletes to improve their health and fitness. Celebrate the natural and cultural history of Louisville.
FY 23-26 TIP Funding: | FY 2026 Construction (C) Phase with TA-MPO funds: $3,581,000 (Federal) + $895,250 (Other) = $4,476,250 (Total) FY 2026 Construction (C) Phase with TA-MPO funds: $4,305,000 (Federal) + $1,076,250 (Other) = $5,381,250 (Total)
Project Sponsor: | Louisville Metro | KIPDA ID: | 2896 | State ID: | 5-3011.00
County: | Jefferson | Parent ID: |  | Group ID:
Project Name: | Crums Lane Sidewalk Phase 1 | Funding Source: | CRP-MPO | Open to Public Date: | 2027
Total Estimated Project Cost: | $1,613,723 $1,943,723 |  | Total Cost Programmed in TIP to date: | $1,613,723 $1,943,723
Description: | Construct a continuous 5-foot sidewalk where none currently exists and rehabilitate existing sections of sidewalk on the north side of Crums Lane from Hartlage Court to Dixie Highway. Construct and/or rehabilitate a continuous 5-foot sidewalk on the south side of Crums Lane from North Lane to the existing sidewalk at the edge of 2112 Crums Lane. This project will add and/or rehabilitate approximately 1.1 miles of sidewalk.
Justification: | There are limited pedestrian connections on Crums Lane and they are often not ADA-compliant and in poor condition. This minor arterial connects a principal arterial (Dixie Highway) to a primarily residential corridor. New sidewalks will provide safe and accessible pedestrian connections to the commercial corridor and transit route along Crums Lane and Dixie Highway. A second phase to extend the sidewalk to Cane Run Road will be proposed in the near future.
FY 23-26 TIP Funding: | FY 2025 Right of Way (ROW) phase with TA-MPO funds: $88,978 (Federal) + $22,245 (Other) = $111,223 (Total) FY 2025 Right of Way (ROW) phase with TA-MPO funds: $352,978 (Federal) + $88,245 (Other) = $441,223 (Total) FY 2026 Construction (C) phase with TA-MPO funds: $596,120 (Federal) + $149,090 (Other) = $745,210 (Total)
Project Sponsor: | Louisville Metro | KIPDA ID: | 2539 | State ID: | 5-3034.00
County: | Jefferson | Parent ID: | 1857 | Group ID:
Project Name: | Louisville Loop Shared Use Path - McNeely Lake Segment | Funding Source: | TA-MPO | Open to Public Date: | 2028
Total Estimated Project Cost: | 3674679 |  | Total Cost Programmed in TIP to date: | 3338679
Description: | Construct approximately two miles of new 10-12 foot wide asphalt/concrete shared use path through McNeely Lake Park. The first phase of the new shared use path will connect the recently constructed Loop path at Cedar Creek Road on the southeast side of the park to the existing park path at the west side of the McNeely Lake dam on the north side of the park. This segment of the Louisville Loop in McNeely Lake Park will include a new bridge over the lake at the dam spillway area and a trail head near the east end of the new path. The second phase of the new shared use path will connect the dam spillway area with Copper Chapel Road along the lake. This segment will include a new bridge over the lake near McNeely Lake Park Road.
Justification: | McNeely Lake Park is a major urban park located in the southern part of Louisville which is experiencing a rapid transition from primarily agricultural to low and medium density residential land uses. As Louisville continues to grow in this area, there is a need for better connectivity and accessiblity from both existing and approved new neighborhoods to the recreational amenities in the 746-acre park which includes athletic fields, tennis and basketball courts, a playground, and extensive path and trail system used by pedestrians, cross-country teams and others. The 100-mile Louisville Loop is a shared use path planned to traverse McNeely Lake Park as it moves across the southern part of Louisville from the Jefferson Memorial Forest to the Parklands of Floyds Fork connecting neighborhoods, schools, work places and other community facilities.
FY 23-26 TIP Funding: | FY 2025 Design (D) phase with TA-MPO funds: $242,689 (Federal) + $60,672 (Other) = $303.361 (Total) *FY 2027 Construction (C) phase with TA-MPO funds: $2,000,000 (Federal) + $500,000 (Other) = $2,500,000 (Total) *FY 2027 Construction (C) phase with TA-MPO funds: $5,040,000 (Federal) + $1,260,000 (Other) = $6,300,000 (Total)
Project Sponsor: | KIPDA | KIPDA ID: | 162 | State ID: | 5-384.00
County: | Bullitt, Jefferson, Oldham | Parent ID: |  | Group ID:
Project Name: | KIPDA Regional Rideshare Program - Kentucky | Funding Source: | STBG-MPO | Open to Public Date:
Total Estimated Project Cost: | 50406992 |  | Total Cost Programmed in TIP to date: | 27948655
Description: | The KIPDA Regional Rideshare Program provides ride-matching services, employer-based and regional ridesharing, vanpool subscription services, promotional activities to support ride-sharing, which includes carpooling, vanpooling, taking transit, walking, telecommuting, and bikepooling. This also includes program evaluation and administration.
Justification: | To reduce congestion, improve air quality, and promote sustainability.
FY 23-26 TIP Funding: | FY 2023 Operations phase with STBG-MPO funds: $1,181,346 (Federal) + $295,337 (Other) = $1,476,683 (Total) FY 2024 Operations phase with STBG-MPO funds: $1,204,973 (Federal) + $301,244 (Other) = $1,506,217 (Total) FY 2025 Operations phase with STBG-MPO funds: $997,000 (Federal) + $244,250 (Other) = $1,221,250 (Total) FY 2026 Operations phase with STBG-MPO funds: $996,540 (Federal) + $249,135 (Other) = $1,245,675 (Total) *FY 2027 Operations phase with STBG-MPO funds: $1,016,470 (Federal) + $254,118 (Other) = $1,270,588 (Total) *FY 2028 Operations phase with STBG-MPO funds: $1,036,800 (Federal) + $259,200 (Other) = $1,296,000 (Total) *FY 2029 Operations phase with STBG-MPO funds: $1,057,536 (Federal) + $264,384 (Other) = 1,321,920 (Total)
Project Sponsor: | KYTC | KIPDA ID: | 188 | State ID: | 5-353.00
County: | Jefferson | Parent ID: |  | Group ID:
Project Name: | English Station Road | Funding Source: | STBG-MPO | Open to Public Date: | 2027
Total Estimated Project Cost: | $13,476,300 $18,436,300 |  | Total Cost Programmed in TIP to date: | $13,476,300 $18,436,300
Description: | Widen English Station Road from 2 to 3 lanes (3rd lane will be a center turn lane) from Aiken Road to Avoca Road. The purpose of this project is to provide a wider roadway configuration to improve safety, increase capacity and elevate level of service. Project will improve the safety of the rail crossing and enhance bike and pedestrian network. From MP 0.457 to MP 1.232.
Justification: | The purpose of this project is to provide a wider roadway configuration to improve safety, increase capacity and elevate level of service. Project will improve the safety of the rail crossing and enhance bike and pedestrian network. Due to the two lane configuration and the numerous developments and entrances along the roadway, traffic operations are adversely impacted by vehicles making left turns along this congested corridor. Sight distance in the sag near Chenoweth Run and the crest near the railroad at the northern terminal of the project do not meet the 35 mph design speed criteria. The corridor is a high accident area. The existing roadway surface shows excessive wear with several sections having significant base failures that are not remedied by typical pavement resurfacing. The corridor is heavily traveled by trucks accessing a nearby rock quarry on Old Henry Road and school buses going to the Jefferson Public Schools maintenance facility on East Aiken. Several of the entrances have rutting on the shoulders with drop offs resulting from turning radii not adequate for truck turning movements. Rail crossing is substandard. There are gaps in the bike and pedestrian network. CHAF ID - IP20170032
FY 23-26 TIP Funding: | FY 2025 Construction (C) phase with STBG-MPO funds: $6,408,000 (Federal) +$1,602,000 (Other) = $8,010,000 (Total) FY 2025 Construction (C) phase with STBG-MPO funds: $11,368,000 (Federal) + $2,842,000 (Other) = $14,210,000 (Total)
Project Sponsor: | KYTC | KIPDA ID: | 1879 | State ID: | 5-481.00
County: | Jefferson | Parent ID: |  | Group ID:
Project Name: | KY 864 | Funding Source: | STBG-MPO | Open to Public Date: | 2027
Total Estimated Project Cost: | $20,550,500 $28,688,500 |  | Total Cost Programmed in TIP to date: | $20,427,500 $28,565,500
Description: | KY 864 - Widen Beulah Church Road from 2 to 3 lanes from I-265 to Cedar Creek Road. Project length 1.627 miles. CHAF IP20080206.
Justification: | Improve the access, safety and mobility of Beulah Church Road south of the Gene Snyder Freeway.The Beulah Church Road (KY 864) corridor is a rapidly developing section of Louisville with increasing traffic demand. KY 864 is classified as an urban collector and has many access points. It carries traffic from growing residential suburbs to the Gene Snyder Freeway (I-265) with growth expected to continue. According to the 'Traffic Forecast Report, Jefferson County, Widen KY 864, Item No. 5-481.00', which was published January 25, 2013, the 2012 Average Daily Traffic (ADT) Count was 7,600 vehicles per day (vpd), and the projected 2035 ADT is 9,600 vpd. Additionally, the Cooper Chapel Road extension (5-404.01) to Bardstown Road (US 31E) which is currently under design, is anticipated to bring additional traffic to the route once constructed. Safety is also a primary concern within the project corridor. Between January 2010 and February 2015, there have been 27 collisions in the project corridor, 19 with property damage, and 8 collisions with 11 with injuries.
FY 23-26 TIP Funding: | FY 2025 Construction (C) phase with STBG-MPO funds: $9,150,000 (Federal) + $2,287,500 (Other) = $11,437,500 (Total) FY 2025 Construction (C) phase with STBG-MPO funds: $17,288,000 (Federal) + $4,322,000 (Other) = $21,610,000 (Total)
Project Sponsor: | KYTC | KIPDA ID: | 213 | State ID: | 5-531.00
County: | Jefferson | Parent ID: |  | Group ID:
Project Name: | KY 1932 | Funding Source: | STBG-MPO | Open to Public Date: | 2026
Total Estimated Project Cost: | $5,323,250 $5,959,250 |  | Total Cost Programmed in TIP to date: | $5,323,250 $5,959,250
Description: | Improve the safety and congestion of KY 1932 (Chenoweth Lane) from US 60 (Shelbyville Road) to US 42 (Brownsboro Road). Approximately 1.07 miles (2014BOP).
Justification: | CHAF Purpose: The purpose of the Chenoweth Lane project - from the CSX railroad (just north of Shelbyville Road) to Brownsboro Road is to 1) Improve sight distance and safety for all users, 2) Improve drainage along the corridor and 3) Improve pedestrian safety and mobility. CHAF Need: The needs stem from a higher than average crash rate in the southern section, pedestrian strike history, sight distance obstructions, obstructions in the clear zones, inadequate drainage in the corridor, substandard shoulders, and narrow (east side) and incomplete (west side) sidewalks that do not meet Americans with Disabilities Act of 1990 (ADA) compliance.
FY 23-26 TIP Funding: | FY 2025 Construction (C) phase with STBG-MPO funds: $1,940,000 (Federal) + $485,000 (Other) = $2,425,000 (Total) FY 2025 Construction (C) phase with STBG-MPO funds: $2,576,000 (Federal) + $644,000 (Other) = $3,220,000 (Total)
Project Sponsor: | KYTC | KIPDA ID: | 1271 | State ID: | 5-441.01
County: | Oldham | Parent ID: |  | Group ID:
Project Name: | US 42 | Funding Source: | STBG-MPO | Open to Public Date: | 2027
Total Estimated Project Cost: | 11755000 |  | Total Cost Programmed in TIP to date: | 11755000
Description: | Reconstruct US 42 and widen from 2 lanes to 3 lanes (3rd lane will be a center turn lane) from Jefferson/Oldham County Line to Ridgemoor Drive. Project will include the consideration of improvements to the Hayfield Way intersection (2004BOPC). CHAF ID: IP20080245.
Justification: | The purpose of the project is to improve traffic flow, minimize congestion, and address safety issues on US 42 between the Jefferson County/Oldham County line and Ridgemoor Drive. Due to an increase in commuters to and from Louisville and the development along the project corridor, the traffic volumes are expected to double in the next 20 years. The accident data for the last 3 years shows that there are between 10 and 14 rear end crashes between Hunters Ridge and Ridgemoor Drive each year. The existing profile along this stretch of US 42 contains vertical geometric deficiencies for the posted speed of 45 MPH and has a critical crash rate factor greater than 1.0 (which indicates, statistically, a higher rate than roads of similar functional classifications).
FY 23-26 TIP Funding: | FY 2023 Right of Way (ROW) phase with STBG-MPO funds: $180,000 (Federal) + $36,000 (Other) = $216,000 (Total) FY 2025 Design (D) phase with STBG-MPO funds: $448,000 (Federal) + $112,000 (Other) = $560,000 (Total) FY 2025 Utilities (U) phase with STBG-MPO funds: $1,520,000 (Federal) + $380,000 (Other) = $1,900,000 (Total) FY 2025 Construction (C) phase with STBG-MPO funds: $5,020,000 (Federal) + $1,255,000 (Other) = $6,275,000 (Total)
Project Sponsor: | Louisville Metro | KIPDA ID: | 337 | State ID: | 5-965.15
County: | Jefferson | Parent ID: |  | Group ID:
Project Name: | Bicycle & Pedestrian Education, Encouragement, Enforcement & Evaluation | Funding Source: | STBG-MPO | Open to Public Date:
Total Estimated Project Cost: | $3,148,194 $3,628,194 |  | Total Cost Programmed in TIP to date: | $3,148,194 $3,628,194
Description: | Development of educational and awareness programs concerning bicycle and pedestrian issues. Provide education and training for cyclists, motorists, and city officials about laws governing cyclists' rights and responsibilities
Justification: | Bicycle and pedestrian projects may provide traffic congestion relief, improve air quality and provide safety for bicyclists and pedestrians. Project will increase awareness of bicycling and walking as an alternative to vehicle trips. This project is an essential component to meeting goals of increased biking and walking trips while decreasing related injuries and deaths.
FY 23-26 TIP Funding: | FY 2023 Operations phase with STBG-MPO funds: $120,000 (Federal) + $30,000 (Other) = $150,000 (Total) FY 2024 Operations phase with STBG-MPO funds: $120,000 (Federal) + $30,000 (Other) = $150,000 (Total) FY 2025 Operations phase with STBG-MPO funds: $120,000 (Federal) + $30,000 (Other) = $150,000 (Total) FY 2026 Operations phase with STBG-MPO funds: $120,000 (Federal) + $30,000 (Other) = $150,000 (Total) FY 2026 Operations phase with STBG-MPO funds: $150,000 (Federal) + $37,500 (Other) = $187,500 (Total) *FY 2027 Operations phase with STBG-MPO funds: $150,000 (Federal) + $37,500 (Other) = $187,500 (Total) *FY 2028 Operations phase with STBG-MPO funds: $150,000 (Federal) + $37,500 (Other) = $187,500 (Total) *FY 2029 Operations phase with STBG-MPO funds: $150,000 (Federal) + $37,500 (Other) = $187,500 (Total)
Project Sponsor: | Louisville Metro | KIPDA ID: | 223 | State ID: | 5-404.01
County: | Jefferson | Parent ID: |  | Group ID:
Project Name: | Cooper Chapel Road Phase 3 | Funding Source: | STBG-MPO | Open to Public Date: | 2025 2028
Total Estimated Project Cost: | 30699792 |  | Total Cost Programmed in TIP to date: | 29610703
Description: | Phase 3: Extend and construct 2 lane roadway with a continuous center-turn lane from KY 864 (Beulah Church Road) to US 31E (Bardstown Road) at Bardstown Falls Road. Project will include consideration of bicycle and pedestrian facilities.
Justification: | The area south of I-265 (Gene Snyder Fwy.) between KY 61 (Preston Highway) and US 31E (Bardstown Road) is experiencing rapid growth with the development of many new residential subdivisions. Cooper Chapel Road is a heavily traveled collector road serving this area. The Location and Feasibility Study will establish and preserve a corridor for the future extension of Cooper Chapel Road so that it can be established as a through route between KY 61 and US 31E. The roadway construction will provide access to an area that recently received sanitary sewers and city water service.
FY 23-26 TIP Funding: | FY 2024 Design (D) phase with STBG-MPO funds: $65,080 (Federal) + $16,270 (Other) = $81,350 (Total) FY 2024 Right of Way (ROW) phase with STBG-MPO funds: $779,400 (Federal) + $194,850 (Other) = $974,250 (Total) FY 2025 Utilities (U) phase with STBG-MPO funds: $1,500,000 (Federal) + $375,000 (Other) = $1,875,000 (Total) FY 2025 Utilities (U) phase with STBG-MPO funds: $2,098,400 (Federal) + $524,600 (Other) = $2,623,000 (Total) FY 2025 Construction (C) phase with STBG-MPO funds: $16,000,000 (Federal) + $4,000,000 (Other) = $20,000,000 (Total) *FY 2027 Construction (C) phase with STBG-MPO funds: $18,153,600 (Federal) + $4,538,400 (Other) = $22,692,000 (Total)
Project Sponsor: | APCD | KIPDA ID: | 369 | State ID:
County: | Bullitt, Jefferson, Oldham | Parent ID: |  | Group ID:
Project Name: | Kentuckiana Air Education | Funding Source: | STBG-MPO | Open to Public Date:
Total Estimated Project Cost: | 6992000 |  | Total Cost Programmed in TIP to date: | 6992000
Description: | Information/outreach campaign to educate public about air quality issues and encourage the public to make air-friendly choices.
Justification: | Reduce ozone levels in Louisville ozone maintenance area. Raise public awareness of connections between transportation and air quality and influence positive behavior.
FY 23-26 TIP Funding: | FY 2023 Operations phase with STBG-MPO funds: $200,000 (Federal) + $50,000 (Other) = $250,000 (Total) FY 2024 Operations phase with STBG-MPO funds: $200,000 (Federal) + $50,000 (Other) = $250,000 (Total) FY 2025 Operations phase with STBG-MPO funds: $200,000 (Federal) + $50,000 (Other) = $250,000 (Total) FY2026 Operations phase with STBG-MPO funds: $200,000 (Federal) + $50,000 (Other) = $250,000 (Total) *FY 2027 Operations phase with STBG-MPO funds: $200,000 (Federal) + $50,000 (Other) = $250,000 (Total) *FY 2028 Operations phase with STBG-MPO funds: $200,000 (Federal) + $50,000 (Other) = $250,000 (Total) *FY 2029 Operations phase with STBG-MPO funds: $200,000 (Federal) + $50,000 (Other) = $250,000 (Total)
Project Sponsor: | Louisville Metro | KIPDA ID: | 3233 | State ID: | 5-479.10
County: | Jefferson | Parent ID: |  | Group ID:
Project Name: | North Hubbards Lane | Funding Source: | STBG-MPO | Open to Public Date: | 2025
Total Estimated Project Cost: | $5,611,987 $7,371,987 |  | Total Cost Programmed in TIP to date: | $5,611,987 $7,371,987
Description: | Widen Hubbards Lane from 2 to 3 lanes (3rd lane will be a center turn lane) including bicycle and pedestrian facilities from US 60 (Shelbyville Road) to KY 1447 (Westport Road).
Justification: | Hubbards Lane is a heavily traveled collector which passes through residential development between US 60 and US 42.
FY 23-26 TIP Funding: | FY 2023 Design (D) phase with Local funds: $0 (Federal) + $110,000 (Other) = $110,000 (Total) FY 2024 Utilities (U) phase with STBG-MPO funds: $749,589 (Federal) + $187,398 (Other) = $936,987 (Total) FY 2025 Construction (CN) phase with STBG-MPO funds: $3,740,000 (Federal) + $825,000 (Other) = $4,565,000 (Total) FY 2025 Construction (C) phase with STBG-MPO funds: $5,809,589 (Federal) + $1,452,398 (Other) = $7,261,987 (Total)
Project Sponsor: | Louisville Metro | KIPDA ID: | 2271 | State ID: | 5-3030.40
County: | Jefferson | Parent ID: | 1856 | Group ID:
Project Name: | Northeast Louisville Loop MET Section 4 | Funding Source: | STBG-MPO | Open to Public Date: | 2030
Total Estimated Project Cost: | 1956500 |  | Total Cost Programmed in TIP to date: | $712,500 $1,816,900
Description: | Construct a shared-use path along US 60 (Shelbyville Road) from Beckley Creek Park to Eastwood Cut-off, 0.6 miles.
Justification: | To improve pedestrian and bicycling access.
FY 23-26 TIP Funding: | FY 2023 Right of Way (ROW) phase with STBG-MPO funds: $350,000 (Federal) + $87,500 (Other) = $437,500 (Total) FY 2027 Utilities (U) phase with STBG-MPO funds: $220,000 (Federal) + $55,000 (Other) = $275,000 (Total) FY 2026 Construction (C) phase with STBG-MPO funds: $1,103,520 (Federal) + $275,880 (Other) = $1,379,400 (Total)
Project Sponsor: | Louisville Metro | KIPDA ID: | 1809 | State ID: | 5-470.00
County: | Jefferson | Parent ID: |  | Group ID:
Project Name: | One-Way Street Conversion to Two-Way Phase 1 | Funding Source: | STBG-MPO | Open to Public Date: | 2024 2027
Total Estimated Project Cost: | $7,211,300 $18,741,300 |  | Total Cost Programmed in TIP to date: | $7,211,300 $18,741,300
Description: | Design and construction for the conversion of the following one-way streets in downtown Louisville to two-way traffic flow: Jefferson Street (Floyd to Baxter Avenue); Liberty Street (Jackson to Baxter); Muhammad Ali Boulevard (Jackson to Chestnut Connector); Chestnut Street (Jackson to Chestnut Connector); 8th Street (Kentucky to Main); 7th Street (Oak to Main); Shelby Street (Gray to Main Street); and Campbell Street (Chestnut to Main Street).
Justification: | One-way streets make for efficient movers of traffic, but can often introduce safety concerns for motorists, bicyclists and pedestrians because they tend to provide for higher travel speeds than two-way streets and in some cases hinder opportunities for economic development as certain businesses have a formal policy against locating on one-way streets. The benefits of two-way streets are numerous. They tend to have slower travel speeds than one-way streets, they reduce confusion for motorists unfamiliar with the area, they provide better access to both businesses and residential areas, and in some circumstances they can reduce the traffic load on other one-way streets.
FY 23-26 TIP Funding: | FY 2023 Utilities (U) phase with STBG-MPO funds: $220,000 (Federal) + $50,000 (Other) = $270,000 (Total) FY 2025 Design (D) phase with STBG-MPO funds: $219,900 (Federal) + $54,975 (Other) = $274,875 (Total) FY 2024 Construction (C) phase with STBG-MPO funds: $1,650,000 (Federal) + $412,500 (Other) = $2,062,500 (Total) FY 2026 Construction (C) phase with STBG-MPO funds: $10,874,000 (Federal) + $2,843,500 (Other) = $13,717,500 (Total)
Project Sponsor: | Oldham County | KIPDA ID: | 3141 | State ID: | 5-596.00
County: | Oldham | Parent ID: |  | Group ID:
Project Name: | KY 22/Clore Lane Intersection Improvements | Funding Source: | STBG-MPO | Open to Public Date: | 2027
Total Estimated Project Cost: | 4475557 |  | Total Cost Programmed in TIP to date: | 4475557
Description: | This project will align Wooldridge Avenue and Clore Lane with left-turn lanes and right-turn pockets on both streets as well as add dedicated left-turn lanes on KY 22. Trees and vegetation will be cleared for increased visibility.
Justification: | The KY 22 Corridor Improvement Study completed by Oldham County, KYTC and KIPDA in 2022, looked at KY 22 from the Jefferson/Oldham County line near Haunz Lane to KY 329. This project was identified in the study as the highest priority spot improvement. This intersection had the highest number of total crashes, more severe crashes, and the highest crash factor (1.58) of all intersections studied. It was also the top safety concern identified during two rounds of public engagement.
FY 23-26 TIP Funding: | FY 2024 Design (D) phase with STBG-MPO funds: $188,889 (Federal) + $47,223 (Other) = $236,112 (Total) FY 2025 Design (D) phase with STBG-MPO funds: $147,111 (Federal) + $36,777 (Other) = $183,888 (Total) FY 2025 Right of Way (ROW) phase with STBG-MPO funds: $733,333 (Federal) + $183,334 (Other) = $916,667 (Total) FY 2026 Utilities (U) phase with STBG-MPO funds: $622,222 (Federal) + $155,556 (Other) = $777,778 (Total) *FY 2027 Construction (C) phase with STBG-MPO funds: $1,888,889 (Federal) + $472,223 (Other) = $2,361,112 (Total) *FY 2028 Construction (C) phase with STBG-MPO funds: $1,888,889 (Federal) + $472,223 (Other) = $2,361,112 (Total)
Project Sponsor: | Jeffersontown | KIPDA ID: | 3111 | State ID:
County: | Jefferson | Parent ID: |  | Group ID:
Project Name: | Billtown-Eastview Collector Extension | Funding Source: | STBG-MPO | Open to Public Date: | 2026 2030
Total Estimated Project Cost: | $1,265,000 $2,352,000 |  | Total Cost Programmed in TIP to date: | $1,265,000 $2,352,000
Description: | Improve safety, improve multi-modal connectivity, and reduce congestion along Billtown Road (CS-1720H) from Ruckreigel Parkway (MP 0.000) to Watterson Trail (MP 0.165). Improve access and multi-modal connectivity from Billtown Road to Eastview Avenue. The project includes the 3-lane widening of existing Billtown Road between Ruckreigel Parkway and Watterson Trail, and the addition of curb and gutter and sidewalks along both sides of the road. The project also includes the extension of existing Eastview Avenue between Billtown and Taylorsville Road, where some segments of narrow roadway and right of way already exist. The Eastview extension will be a 2-lane curb and gutter roadway with sidewalks and will help to establish improved access and connectivity for the new Jeffersontown Police Station to be completed in 2023.
Justification: | The project helps to complete Jeffersontown’s downtown transportation plan and establish additional points of system access and connectivity, by linking Taylorsville Road and Billtown Road, as well as a linkage to the existing dead-end portion of College Avenue in between. The extension is most critical to provide enhanced access to the new police station at the corner of Neal and Taylorsville Road and will open up access to the south. The project supports the City’s goal to provide complete streets, through the inclusion of sidewalks along each side of both Billtown and Eastview. Presently, there is a narrow sidewalk, in poor condition, and with no vertical curb separation from the road, along one side of the Billtown corridor. The Eastview extension crosses a 2+ acre vacant parcel owned by the City. Thus, the right of way acquisition costs will be limited, and the project will help to create economic development opportunities to support the future land use plan for the vacant property.
FY 23-26 TIP Funding: | FY 2026 Design (D) Phase with STBG-MPO Funds: $310,000 (Federal) + $70,400 (State/Local) = $380,400 (Total) FY 2026 Construction (CN) Phase with STBG-MPO Funds: $660,000 (Federal) + $165,000 (State/Local) = $825,000 (Total) *FY 2027 Right of Way (ROW) Phase with STBG-MPO Funds: $176,000 (Federal) + $40,000 (State/Local) = $216,000 (Total) *FY 2028 Utilities (U) Phase with STBG-MPO Funds: $528,000 (Federal) + $120,000 (State/Local) = $648,000 (Total) *FY 2029 Construction (CN) Phase with STBG-MPO Funds: $1,056,000 (Federal) + $240,000 (State/Local) = $1,296,000 (Total)
Project Sponsor: | Jeffersontown | KIPDA ID: | 3113 | State ID:
County: | Jefferson | Parent ID: |  | Group ID:
Project Name: | Galene Drive/Sprowl Road Collector Extension | Funding Source: | STBG-MPO | Open to Public Date: | 2028 2030
Total Estimated Project Cost: | 8080000 |  | Total Cost Programmed in TIP to date: | 8080000
Description: | Improve capacity, connectivity, and multi-modal safety along Galene Drive (CS-1010H) from Maple Road (MP 1.134) to Bluebird Lane. The project includes realigning Galene Drive/Sprowl Road, and extending this connection east, widening the collector roadway curb and gutters, and adding sidewalks and bicycle facilities. Project will include turning movements and signalization as warranted.
Justification: | The project includes a new roadway, minor roadway widening, and intersection improvements to accomplish multiple transportation goals for the City of Jeffersontown. The realignment of the Galene/Sprowl intersection with College Dr addresses a poorly configured offset intersection where vehicular and pedestrian traffic safety at the adjacent Tully Elementary School has long been an issue. The realignment of this critical intersection is the primary focus of the project west of Taylorsville Rd. East of Taylorsville Rd, the project serves as a critical new connector, providing multiple linkages to the local transportation system at Shelby Street and Bluebird Lane which both connect south to Watterson Trail, and at residential dead-end streets of Valley and Pelham, which both connect north to Grand Avenue. In addition to multi-modal connectivity, this eastern portion of the corridor also provides for some areas of economic development opportunities which will also serve to benefit the community.
FY 23-26 TIP Funding: | FY 2025 Planning (P) phase with STBG-MPO funds: $264,000 (Federal) + $66,000 (Other) = $330,000 (Total) FY 2026 Planning (P) phase with STBG-MPO funds: $264,000 (Federal) + $66,000 (Other) = $330,000 (Total) FY 2025 Design (D) phase with STBG-MPO funds: $440,000 (Federal) + $110,000 (Other) = $550,000 (Total) FY 2027 Design (D) phase with STBG-MPO funds: $440,000 (Federal) + $110,000 (Other) = $550,000 (Total) FY 2026 Right of Way (ROW) phase with STBG-MPO funds: $880,000 (Federal) + $220,000 (Other) = $1,100,000 (Total) FY 2028 Right of Way (ROW) phase with STBG-MPO funds: $880,000 (Federal) + $220,000 (Other) = $1,100,000 (Total) FY 2026 Utilities (U) phase with the STBG-MPO funds: $440,000 (Federal) + $110,000 (Other) = $550,000 (Total) FY 2027 Construction (C) phase with the STBG-MPO funds: $4,440,000 (Federal) + $1,110,000 (Other) = $5,550,000 (Total) FY 2029 Utilities (U) phase with the STBG-MPO funds: $440,000 (Federal) + $110,000 (Other) = $550,000 (Total) FY 2029 Construction (C) phase with the STBG-MPO funds: $4,440,000 (Federal) + $1,110,000 (Other) = $5,550,000 (Total)
Project Sponsor: | Mount Washington | KIPDA ID: | 2479 | State ID: | 5-3216.00
County: | Bullitt | Parent ID: |  | Group ID:
Project Name: | Historic Multi-Use Trail Segment C | Funding Source: | STBG-MPO | Open to Public Date: | 2026
Total Estimated Project Cost: | 4763002 |  | Total Cost Programmed in TIP to date: | 4763002
Description: | Construct multi-use path and pedestrian walkway along segment C of the Historic Memorial Multi-Use Trail including a Rest Plaza at Landis Lane and US 31EX. In addition, improve safety along the segment by reducing drainage hazards and installing a roundabout at Landis Lane.
Justification: | To improve bicycle and pedestrian transportation within Mount Washington including safety elements. These facilities will be accompanied by a new signal on the north end of the project at Landis Lane in order to safely get pedestrian traffic from the east sidewalk to the west multi-use path and the connecting rest plaza and other trails.
FY 23-26 TIP Funding: | FY 2023 Design (D) phase with STBG-MPO funds: $79,172 (Federal) + $19,793 (Other) = $98,965 (Total) FY 2023 Right of Way (ROW) phase with STBG-MPO funds: $497,630 (Federal) + $124,408 (Other) = $622,038 (Total) FY 2025 Construction (C) phase with STBG-MPO funds: $1,460,012 (Federal) + $365,003 (Other) = $1,825,015 (Total) FY 2025 Construction (C) phase with TA-MPO funds: $870,787 (Federal) + $217,697 (Other) = $1,088,484 (Total) FY 2025 Construction (C) phase with STBG-MPO funds: $2,330,799 (Federal) + $582,700 (Other) = $2,913,499 (Total) FY 2025 Construction (C) phase with STGB-ST funds: $118,000 (Federal) + $29,500 (Other) = $147,5000 (Total)
Project Sponsor: | Oldham County | KIPDA ID: | 2175 | State ID: | 5-410.01
County: | Oldham | Parent ID: | 327 | Group ID:
Project Name: | Old LaGrange Road Improvements Oldham County Bicycle & Pedestrian Trail | Funding Source: | STBG-MPO | Open to Public Date: | 2027
Total Estimated Project Cost: | $2,600,000 $3,797,979 |  | Total Cost Programmed in TIP to date: | $2,600,000 $3,797,979
Description: | Construct a bicycle and pedestrian trail section along Old LaGrange Road from North Camden Lane to the KY 329 Bypass and on to the intersection with KY 146 in Crestwood.
Justification: | To provide improved access for pedestrians and bicyclists along Old LaGrange Road.
FY 23-26 TIP Funding: | FY 2024 Right of Way phase (ROW) with STBG-MPO funds: $239,676 (Federal) + $59,919 (Other) = $299,595 (Total) FY 2024 Right of Way phase (ROW) with STBG-ST funds: $340,324 (Federal) + $85,081 (Other) = $425,405 (Total) FY 2025 Utilities (U) phase with STBG-MPO funds: $750,000 (Federal) + $187,500 (Other) = $937,500 (Total) FY 2026 Construction (C) phase with STBG-MPO funds: $500,000 (Federal) + $125,000 (Other) = $625,000 (Total) FY 2026 Construction (C) phase with STBG-MPO funds: $1,458,383 (Federal) + $364,596 (Other) = $1,822,979 (Total)
Project Sponsor: | Bullitt County | KIPDA ID: | New | State ID:
County: | Bullitt | Parent ID: |  | Group ID:
Project Name: | US 31E to KY 2706 | Funding Source: | STBG-MPO | Open to Public Date: | 2033
Total Estimated Project Cost: | 18000000 |  | Total Cost Programmed in TIP to date: | 250000
Description: | Widening KY 2706 (Greenbrier Rd.) from HWY 44 to 31Ex and eventually extending to 31E. KY 2706 would include Wales Run and Landis Lane, intersecting with 31EX.
Justification: | High growth area in Mt Washington, with possible economic and residential impact. Also parks and recreation benefits
FY 23-26 TIP Funding: | FY 2026 Planning (P) phase with STBG-MPO funds: $200,000 (Federal) + $50,000 (Other) = $250,000 (Total)
Project Sponsor: | TARC | KIPDA ID: | New | State ID:
County: | Jefferson | Parent ID: |  | Group ID:
Project Name: | Louisville Downtown Transit Center | Funding Source: | STBG-MPO | Open to Public Date: | 2031
Total Estimated Project Cost: | 16000000 |  | Total Cost Programmed in TIP to date: | 1250000
Description: | The Louisville Downtown Transit Center project would include two phases: (1) Establish operational specifications for a downtown transit center, identify potential locations, design line-level routing through downtown, facilitate stakeholder engagement and community input around the project, provide high level cost assumptions for land acquisition, design, and construction, and fund preliminary design documents. (2) Funding for engineering and construction of a Downtown Transit Center.
Justification: | Transit centers provide critical, centralized infrastructure to transit users at high activity locations. These can include purchasing passes, transfering between routes, providing convenient locations for operators to relieve other operators, and other opportunities to enhance the transit experience. Transit centers consolidate services to a single location, increasing regional access to jobs and social services and improve operations. Transit centers can integrate other community amenities such as commercial space, public wi-fi, and restrooms for operators.
FY 23-26 TIP Funding: | FY 2027 Design (D) phase with STBG-MPO funds: $1,000,000 (Federal) + $250,000 (Other) = $1,250,000 (Total)

## IN Approved Funding Changes
Project Sponsor: | APCD | KIPDA ID: | New | State ID:
County: | Clark, Floyd | Parent ID: | 370 | Group ID: | N/A
Project Name: | Kentuckiana Air Education 2030 | Funding Source: | CMAQ-MPO | Open to Public Date: | 2030
Total Estimated Project Cost: | 250000 |  | Total Cost Programmed in TIP to date: | 250000
Description: | Kentuckiana Air Education (KAIRE) is an air pollution prevention and awareness program that will increase public awareness of the impacts individual choices can have on local air quality.
Justification: | KAIRE works to encourage voluntary air quality changes through community involvement, increasing public awareness of the impacts individual choices can have on local air quality.
FY 23-26 TIP Funding: | *FY 2030 Operations phase with CMAQ-MPO funds: $200,000 (Federal) + $50,000 (Other) = $250,000 (Total)
Project Sponsor: | New Albany | KIPDA ID: | 3136 | State ID: | 2301550
County: | Floyd County | Parent ID: | N/A | Group ID: | N/A
Project Name: | Intersection of East Spring Street and Beharrell Avenue | Funding Source: | Group III & HSIP-MPO | Open to Public Date: | 2029
Total Estimated Project Cost: | 3230000 |  | Total Cost Programmed in TIP to date: | 2871112
Description: | Improvement of the intersection of East Spring Street (a major arterial and gateway into the community with Beharrell Avenue (a collector class roadway). The concept is to utilize a roundabout, a proven safety counter measure, in order to improve the safety of this intersection, slow traffic entering the City of New Albany, and to enhance the livability and walkability of the surrounding areas of the community. This would also allow for a connection to the Ohio River Greenway, and provide a road diet on Spring Street that will accommodate bicycle facilities, parking, and other amenities for the community which will make this corridor more functional for all citizens and not solely drivers. The cost estimate for these intersection improvements is $3,230,000.
Justification: | The City of New Albany is always looking to improve the safety of our roadways and intersections. The current configuration of East Spring Street effectively bisects the neighborhood along Beharrell Avenue. This project will reunite the community, improve safety, improve walkability, improve quality of place and life, all while utilizing a proven safety counter measure that is championed by the FHWA. Furthermore, this project will connect neighborhoods to the north of East Spring Street with the vital community asset that is the Ohio River Greenway.
FY 23-26 TIP Funding: | FY 2025 Preliminary Engineering (PE) phase with HSIP-MPO Funds: $25,200 (Federal) + $28,000 (Other) = $280,000 (Total) FY 2025 Preliminary Engineering (PE) phase with HSIP-MPO Funds: $252,000 (Federal) + $28,000 (Other) = $280,000 (Total) *FY 2027 Right of Way (ROW) phase with HSIP-MPO Funds: $400,000 (Federal) + $44,445 (Other) = $444,445 (Total) *FY 2028 Right of Way (ROW) phase with HSIP-MPO Funds: $400,000 (Federal) + $44,445 (Other) = $444,445 (Total) *FY 2029 Construction (CN) phase with HSIP-MPO Funds: $1,932,000 (Federal) + $214,667 (Other) = $2,146,667 (Total)
Project Sponsor: | Floyd County Board of Commissioners | KIPDA ID: | 1558 | State ID: | 1700788
County: | Clark, Floyd | Parent ID: | N/A | Group ID: | 2676
Project Name: | Replacement of Bridge 51 | Funding Source: | STBG-MPO | Open to Public Date: | 2027
Total Estimated Project Cost: | $7,000,000 $7,967,060 |  | Total Cost Programmed in TIP to date: | $6,613,708 $7,580,768
Description: | Replacement of Bridge 51 over Silver Creek and reconstruction of approaches on Blackiston Mill Road. Total project length is approximately 0.312 miles.
Justification: | The proposed replacement bridge will be approximately 250 feet long, with 700 foot approaches. Bridge 51 carries Blackiston Mill Road over Silver Creek and currently serves as a critical link between the City of New Albany and the Town of Clarksville. The bridge structure itself is the responsibility of Floyd County, with the northern approach being in the City of New Albany and the southern approach in the Town of Clarksville and Clark County. In our 2018 Bridge Inspection Report, Bridge 51 scored a 39.2 Sufficiency Rating.
FY 23-26 TIP Funding: | FY 2024 Preliminary Engineering (PE) phase with STBG-MPO Funds: $202,688 (Federal) + $50,672 (Other) = $253,360 FY 2024 Right of Way (ROW) phase with STBG-MPO Funds: $997,312 (Federal) + $249,328 (Other) = $1,246,640 (Total) FY 2025 ROW phase with STBG-MPO Funds: $158,348 (Federal) + $39,587 (Other) = $197,935 (Total) FY 2026 Construction Engineering (CE) phase with STBG-MPO Funds: $480,000 (Federal) + $120,000 (Other) = $600,000 (Total) FY 2026 Construction (CN) phase with STBG-MPO Funds: $3,608,183 (Federal) + $1,000,000 (Other) = $4,608,183 (Total) FY 2026 Construction (CN) phase with STBG-MPO Funds: $4,095,243 (Federal) + $1,023,811 (Other) = $5,119,054 (Total)
Project Sponsor: | Clarksville | KIPDA ID: | 3018 | State ID: | 2300582
County: | Clark County | Parent ID: | N/A | Group ID: | N/A
Project Name: | Progress Way Improvements | Funding Source: | Group III & STBG-MPO | Open to Public Date: | 2028
Total Estimated Project Cost: | $6,250,000 $8,068,074 |  | Total Cost Programmed in TIP to date: | 6375000
Description: | The project will install new curb and gutter, sidewalks, and drainage along Progress Way from I-65 to Broadway. The width of the lanes will not change, instead they will be shifted south slightly to allow for drainage improvements.
Justification: | The Town is seeing significant growth along Progress Way. This includes the addition of Cunningham Campers and a large apartment complex, both near the Addmore Lane Intersection. The area is already well traveled as a bypass around Veteran's Parkway and the additional apartments will increase the traffic on the roadway. There is not a need for capacity, but instead a need to increase safety along the roadway. The road lacks drainage, curbs, gutters and a walking path. These are needed to increase safety along the entire corridor. The area west of Sam Gwin is highly traveled by individuals living in the Senior Housing along Greentree North. They often travel in and cross the roadway in their motorized scooters. This very unsafe and the proposed improvements will give them a place to safely cross and travel.
FY 23-26 TIP Funding: | FY 2025 Right of Way (ROW) phase with STBG-MPO Funds: $300,000 (Federal) + $75,000 (Other) = $375,000 (Total) FY 2025 Right of Way (ROW) phase with Group III Funds: $100,000 (Federal) + $25,000 (Other) = $125,000 (Total) *FY 2027 Utilities (U) phase with STBG-MPO Funds: $700,000 (Federal) + 175,000 (Other) = $875,000 (Total) *FY 2027 Construction (CN) phase with STBG-MPO Funds: $1,817,926 (Federal) + $3,182,074 (Other) = $5,000,000 (Total) *FY 2027 Cosntruction Engineering (CE) phase with STBG-MPO Funds: $336,000 (Federal) + $84,000 (Other) = $420,000 (Total) *FY 2027 Construction (CN) phase with STBG-MPO Funds: $3,200,000 (Federal) + $800,000 (Other) = $4,000,000 (Total)
Project Sponsor: | Floyd County | KIPDA ID: | 3102 | State ID: | 2301317
County: | Floyd | Parent ID: | N/A | Group ID: | N/A
Project Name: | Graybrook Lane Extension | Funding Source: | STBG-MPO | Open to Public Date: | 2031
Total Estimated Project Cost: | 3708432 |  | Total Cost Programmed in TIP to date: | 3708432
Description: | Extension of collector class roadway (Graybrook Lane) from the intersection with Bono Road/Pearl Street to the intersection of State Street. This roadway extension would further establish connections from economically depressed areas to the vital State Street corridor.
Justification: | Graybrook Lane currently deadends into Pearl Street/Bono Road intersection. By extending Graybrook Lane, the collector class roadway would be extended to an important arterial roadway of State Street which would allow citizens an easier route to connect to shopping, vital services, and transit. Furthermore, this project serves an economically depressed area of the city and would allow better connections for the citizens adjacent to this project.
FY 23-26 TIP Funding: | FY 2025 Preliminary Engineering (PE) phase with STBG-MPO funds: $357,109 (Federal) + $108,636 (Other) = $465,745 (Total) *FY 2028 Right of Way (ROW) phase with STBG-MPO funds: $439,200 (Federal) + $109,800 (Other) = $549,000 (Total) *FY 2029 Utilitities (U) phase with STBG-MPO funds: $80,000 (Federal) + $20,000 (Other) = $100,000 (Total) *FY 2030 Construction (CN) phase with STBG-MPO funds: $2,074,949 (Federal) + $518,738 (Other) = $2,593,687 (Total)
Project Sponsor: | KIPDA | KIPDA ID: | New | State ID:
County: | Clark, Floyd | Parent ID: | 56 | Group ID: | N/A
Project Name: | KIPDA Regional Rideshare Program - Indiana FY 2030 | Funding Source: | STBG-MPO | Open to Public Date: | 2030
Total Estimated Project Cost: | 158750 |  | Total Cost Programmed in TIP to date: | 158750
Description: | The KIPDA Regional Rideshare program provides ride-matching services, employer-based and regional ridesharing, vanpool subscription services, promotional activities to support ride-sharing, which includes carpooling, vanpooling, and bikepooling. This also includes program evaluation and administration.
Justification: | To reduce congestion, improve air quality, and promote sustainability.
FY 23-26 TIP Funding: | *FY 2030 Operations phase with STBG-MPO funds: $127,000 (Federal) + $31,750 (Other) = $158,750 (Total)
Project Sponsor: | Clark County | KIPDA ID: | New as of A8 | State ID: | 2401840
County: | Clark | Parent ID: | N/A | Group ID: | N/A
Project Name: | CR-311 and Sellersburg Improvements | Funding Source: | Group III & CMAQ-MPO (MUST GET INDOT APPROVAL BEFORE PUTTING CMAQ FUNDS IN TIP) | Open to Public Date: | 2030
Total Estimated Project Cost: | 11320000 |  | Total Cost Programmed in TIP to date: | 750000
Description: | Corridor improvements will extend along CR-311 from SR-60 to US-31 in Sellersburg. Project will add sidewalks, a bike path and a center turn lane to provide safe traffic/transportation alternatives and improve overall safety in the area
Justification: | KIPDA Funded Corridor study recommended a center left turn lane for the CR-311. Sellersburg has asked for sidewalks and bike path to provide safe alternative options for residents. Sellersburg is moving most of their town center options to this part of Sellersburg and are requesting the County to help improve the area for their residents.
FY 23-26 TIP Funding: | FY 2025 Preliminary Engineering (PE) phase with Group III Funds: $600,000 (Federal) + $150,000 (Other) = $750,000 (Total) *FY 2027 Right of Way (ROW) phase with CMAQ-MPO Funds: $500,000 (Federal) + $100,000 (Other) = $600,000 (Total) *FY 2028 Right of Way (ROW) phase with CMAQ-MPO Funds: $500,000 (Federal) + $100,000 (Other) = $600,000 (Total) *FY 2029 Utilities (U) phase with CMAQ-MPO Funds: $500,000 (Federal) + $100,000 (Other) = $600,000 (Total)
Project Sponsor: | Clark County | KIPDA ID: | New as of A8 | State ID: | 2401839
County: | Clark | Parent ID: | N/A | Group ID: | N/A
Project Name: | Memphis Blue Lick Roadway Improvements | Funding Source: | Group III | Open to Public Date: | 2031
Total Estimated Project Cost: | 9700000 |  | Total Cost Programmed in TIP to date: | 125000
Description: | This project will enhance the overall capacity of the Memphis Blue Lick Road and the surrounding area, from Crone Road near the I-65 Interchange to the existing Champions Point S/D, 2+ miles to the west. There are potentially four intersections that must be enhanced (one is an INDOT interchange at I-65); potentially two bridge improvement structures and several small structure crossings that will need to be improved along with the roadway widening for the area. The roadway widening shall include pavement drive lane expansion and improved paved shoulders. Bike paths will also be considered for this project.
Justification: | This area is experiencing significant growth. To date there are 6 residential developments that have been platted with over 2500 new residential lots already approved and significantly more potential for the area. Vehicle counts in the area were completed in 2013 and ranged from 800-2000 AVD. new vehicle counts were completed in 2023, and the numbers have increased to 8000-9000 AVD at locations along the Memphis Blue Lick corridor. Residents in the area are concerned with the growth occurring and the potential for new growth in the currently undeveloped areas.
FY 23-26 TIP Funding: | FY 2025 Planning (P) phase with Group III funds: $75,000 (Federal) + $18,750 (Other) = $93,750 (Total) FY 2025 Planning (P) phase with Group III funds: $100,000 (Federal) + $25,000 (Other) = $125,000 (Total)
Project Sponsor: | Floyd County Board of Commissioners | KIPDA ID: | New as of A8 | State ID: | 2401835
County: | Floyd | Parent ID: | N/A | Group ID: | N/A
Project Name: | Bridge 38 (Baylor Wissman Replacement) | Funding Source: | Group III & STBG-MPO | Open to Public Date: | 2031
Total Estimated Project Cost: | 3151000 |  | Total Cost Programmed in TIP to date: | 3151000
Description: | Project will replace existing bridge due to poor geometry and the superstructure and substructure deterioration. It will expand bridge from one to two travel lanes with 2 foot shoulders. Approach will be re-aligned to improve site distance.
Justification: | Existing bridge was constructed in 1950 as one lane crossing and is deteriorating. Bridge provides access to road connecting major subdivisions and provides cross I-64 access to County. Approach has horizontal curve decreasing sight distance and making more unsafe.
FY 23-26 TIP Funding: | FY 2025 Preliminary (PE) phase with Group III Funds: $360,000 (Federal) + $90,000 (Other) = $450,000 (Total) *FY 2027 Right of Way (ROW) phase with STBG-MPO Funds: $32,000 (Federal) + $8,000 (Other) = $40,000 *FY 2029 CE phase with STBG-MPO Funds: $276,000 (Federal) + $69,000 (Other) = $345,000 (Total) *FY 2029 Construction (CN) phase with STBG-MPO Funds: $1,852,000 (Federal) + $463,200 (Other) = $2,316,000 (Total)
Project Sponsor: | Floyd County Board of Commissioners | KIPDA ID: | New as of A8 (Needs HSIP approval from INDOT before we put HSIP in TIP) | State ID: | 2401834
County: | Floyd | Parent ID: | N/A | Group ID: | N/A
Project Name: | Baylor Wissman Hilltop | Funding Source: | Group III & HSIP-MPO | Open to Public Date: | 2031
Total Estimated Project Cost: | 3336344 |  | Total Cost Programmed in TIP to date: | $201,852 $3,336,344
Description: | Project will replace existing roadway to widen lanes to 11 feet in each direction, add 2 foot shoulders with 1 foot aggregate. Additional safety measures including edge striping and curve notices will be included.
Justification: | Crash data and a recent Thoroughfare Study indicated run off road crashes on this roadway. The development of a large subdivision in the Town of Georgetown that will utilize this roadway will increase traffic volume and likelihood of additional incidents.
FY 23-26 TIP Funding: | FY 2025 Preliminary Engineering (PE) with Group III Funds: $161,481 (Federal) + $40,371 (Other) = $201,852 (Total) *FY 2028 Right of Way (ROW) phase with HSIP-MPO Funds: $256,460 (Federal) + $409,174 (Other) = $665,634 (Total) *FY 2030 Construction Engineering (CE) phase with HSIP-MPO Funds: $257,620 (Federal) + $64,405 (Other) = $322,025 (Total) *FY 2030 Construction (CN) phase with HSIP-MPO Funds: $833,320 (Federal) + $1,313,514 (Other) = $2,146,834 (Total)
Project Sponsor: | New Albany | KIPDA ID: | New as of A8 | State ID: | 2401854
County: | Floyd | Parent ID: | N/A | Group ID: | N/A
Project Name: | Slate Run Road Phase II | Funding Source: | Group III & TA-MPO & CRP-MPO | Open to Public Date: | 2031
Total Estimated Project Cost: |  |  | Total Cost Programmed in TIP to date:
Description: | The project consists of the widening of Slate Run Road from Lockwood Drive to Ekin Avenue in New Albany, Indiana. The road is being widened to create new separate bicycle lanes. Curb and gutter will be added to both sides of the roadway, and new sidewalks will be constructed outside of the curb lines.
Justification: | This is phase 2 of an overall project for which phase 1 construction was completed in 2021. Slate Run Road has been a safety issue for the City of New Albany due to speeding motorists and the lack of bicycle and pedestrian facilities. The roadway is highly trafficked by bicycles and pedestrians due to the existence of the Slate Run Elementary School. This project is needed to assist in traffic calming to reduce speeding motorists, as well as provide safe bicycle paths and pedestrian walkways separate and outside of the roadway to reduce the risk of fatalities and injuries along this corridor.
FY 23-26 TIP Funding: | FY 2025 Preliminary Engineering (PE) phase with Group III Funds: $200,000 (Federal) + $50,000 (Other) = $250,000 (Total) *FY 2027 Right of Way (ROW) phase with TA-MPO Funds: $402,940 (Federal) + $100,735 (Other) = $503,675 (Total) *FY 2028 Right of Way (ROW) phase with TA-MPO Funds: $1,293,060 (Federal) + $323,265 (Other) = $1,616,325 (Total) *FY 2030 Construction Engineering (CE) phase with TA-MPO Funds: $400,000 (Federal) + $100,000 (Other) = $500,000 (Total) *FY 2030 Construction (CN) phase with CRP-MPO Funds: $4,080,000 (Federal) + $1,020,000 (Other) = $5,100,000 (Total)
Project Sponsor: | Floyd County | KIPDA ID: | New as of A8 | State ID: | 2401836
County: | Floyd | Parent ID: | N/A | Group ID: | N/A
Project Name: | Highway 150 Break - Highlander Point | Funding Source: | Group III & STBG-MPO | Open to Public Date: | 2030
Total Estimated Project Cost: | 3743989 |  | Total Cost Programmed in TIP to date: | $393,750 $3,743,989
Description: | Establishment of lighted intersection between Old Vincennes Road and West Luther Road on Highway 150 providing additional access to Highlander Point Gateway district.
Justification: | Additional access needed from Highway 150 to alleviate congestion and reduce accidents at Old Vincennes Road intersection. Additionally, will provide access to developing areas on either side of Highway.
FY 23-26 TIP Funding: | FY 2025 Preliminary Engineering (PE) phase with Group III funds: $315,000 (Federal) + $78,750 (Other) = $393,750 (Total) *FY 2028 Construction Engineering (CE) phase with STBG-MPO Funds: $402,029 (Federal) + $100,507 (Other) = $502,536 (Total) *FY 2028 Construction (CN) phase with STBG-MPO Funds: $2,680,191 (Federal) + $670,048 (Other) = $3,350,239 (Total)
Project Sponsor: | TARC | KIPDA ID: | New | State ID:
County: | Jefferson | Parent ID: |  | Group ID: | 2675 & 2674
Project Name: | Downtown Transit Center Planning Study | Funding Source: | STBG-MPO (KY) & STBG-MPO (IN) | Open to Public Date: | 2026
Total Estimated Project Cost: | 625000 |  | Total Cost Programmed in TIP to date: | 625000
Description: | Study of a potential Louisville Downtown Transit Center. The study intends to Establish operational specifications for a downtown transit center, identify potential locations, design line-level routing through downtown, facilitate stakeholder engagement and community input around the project, provide high level cost assumptions for land acquisition, design, and construction
Justification: | Transit centers provide critical, centralized infrastructure to transit users at high activity locations. These can include purchasing passes, transfering between routes, providing convenient locations for operators to relieve other operators, and other opportunities to enhance the transit experience. Transit centers consolidate services to a single location, increasing regional access to jobs and social services and improve operations. Transit centers can integrate other community amenities such as commercial space, public wi-fi, and restrooms for operators.
FY 23-26 TIP Funding: | FY 2025 Planning (P) phase with STBG-MPO (IN) funds: $100,000 (Federal) + $25,000 (Other) = $125,000 (Total) FY 2025 Planning (P) phase with STBG-MPO (KY) funds: $400,000 (Federal) + $100,000 (Other) = $500,000 (Total)